“How can NASA SMD materials be used most effectively with OST organizations?

Recommendation 4.1 (Insert Recommendation 4.1 here)

| Activity | Responsible Person(s) | Schedule & Resources Needed | Expected Outcome | Assessment Strategies |
| --- | --- | --- | --- | --- |
| 4.1 Review existing reports/resources such as the AMNH “after school report”. Ensure diverse groups are represented. | SMD & AS organizations | Need a subcommittee <1 month | List of criteria for selection of materials |  |
| 4.2 Identify selected materials to adapt which suit diverse audiences. | SMD education forums & AS partners | 3 months SMD product developers, AS providers at different levels | Materials to adapt |  |
| 4.3 Develop criteria for the review and revision process that considers diverse audiences. | SMD education forums & AS partners |  | List of criteria |  |
| 4.4 Review and revise materials, recognizing the value of diversity. | SMD & AS organizations | 3-6 months AS orgs (including front-line staff) and national forums | First draft of an adapted product | N/A |
| 4.5 Pilot project regionally in diverse settings. | SMD & AS organizations | At least 6-9 months Training resources | First finished product and a framework for adapting other products | Assess quality and success of implementation and provide a feedback loop to review and revise process (formative evaluation) |
| 4.6 Develop long-term assessment plan for adapted and newly developed materials. | SMD forum leaders (support groups) Consultations w/ AS pros | Schedule: indefinite Outside evaluator? | Tracking useage, quality, relevance | An assessment and plan for administering and analyzing |
| 4.7 Train SMD product developers on adapting materials. Website w/ guidelines to partnering with AS orgs SMD meetings & conferences Include diversity considerations in materials development | SMD & AS organizations | Web developer and resources/links from AS orgs Travel for AS pros Schedule: continual | More SMD people who could adapt materials | Number of materials being adapted |